## Jira_Data
Date | Author | Role | Project | Parent Epic | Parent Epic Summary | Parent Ticket | Parent Summary | Ticket | Summary | Time (h) | Holiday | Status | Started | Weekend
2026-05-04 | Aziz | FE | LIBRB | LIBRB-1200 | [RB][May KYC scope] | LIBRB-1201 | [RB][FE][KYC] May frontend integration | LIBRB-5801 | [RB][FE][KYC] Build customer information form | 5,50 |  | Done | 2026-05-04T09:00:00.000+0100 | FAUX
2026-05-05 | Aziz | FE | LIBRB | LIBRB-1200 | [RB][May KYC scope] | LIBRB-1201 | [RB][FE][KYC] May frontend integration | LIBRB-5802 | [RB][FE][KYC] Integrate customer validation API | 3,00 |  | FIXED | 2026-05-05T09:30:00.000+0100 | FAUX
2026-05-06 | Aziz | FE | LIBRB | LIBRB-1200 | [RB][May KYC scope] | LIBRB-1202 | [RB][FE][KYC] UI corrections | LIBRB-5803 | [UPDATED] [RB][FE][KYC] Fix mobile responsive issues | 4,50 |  | FIXED | 2026-05-06T10:00:00.000+0100 | FAUX
2026-05-07 | Aziz | FE | LIBRB | LIBRB-1210 | [RB][Contacts May improvements] | LIBRB-1211 | [RB][FE][Contacts] UI improvements | LIBRB-5804 | [RB][FE][Contacts] Add Arabic translation fixes | 2,50 |  | FIXED | 2026-05-07T13:00:00.000+0100 | FAUX
2026-05-08 | Aziz | FE | LIBRB | LIBRB-1210 | [RB][Contacts May improvements] | LIBRB-1211 | [RB][FE][Contacts] UI improvements | LIBRB-5805 | [RB][FE][Contacts] Add success notification after save | 4,00 |  | To Be Tested | 2026-05-08T09:15:00.000+0100 | FAUX
2026-05-09 | Aziz | FE | LIBRB |  |  |  |  | LIBRB-5806 | Weekend support for urgent FE issue | 3,00 |  | FIXED | 2026-05-09T10:00:00.000+0100 | VRAI
2026-05-11 | Aziz | FE | LIBRB | LIBRB-1200 | [RB][May KYC scope] | LIBRB-1201 | [RB][FE][KYC] May frontend integration | LIBRB-5807 | [RB][FE][KYC] Refactor KYC stepper component | 4,00 |  | Done | 2026-05-11T09:00:00.000+0100 | FAUX
2026-05-12 | Aziz | FE | LIBRB | LIBRB-1220 | [RB][May Dashboard scope] | LIBRB-1221 | [RB][FE][Dashboard] Analytics pages | LIBRB-5808 | [RB][FE][Dashboard] Create analytics overview page | 5,50 |  | In Progress | 2026-05-12T09:15:00.000+0100 | FAUX
2026-05-13 | Aziz | FE | LIBRB | LIBRB-1220 | [RB][May Dashboard scope] | LIBRB-1221 | [RB][FE][Dashboard] Analytics pages | LIBRB-5809 | [RB][FE][Dashboard] Add real-time notification badge | 3,50 |  | To Be Tested | 2026-05-13T09:30:00.000+0100 | FAUX
2026-05-14 | Aziz | FE | LIBRB | LIBRB-1210 | [RB][Contacts May improvements] | LIBRB-1211 | [RB][FE][Contacts] UI improvements | LIBRB-5810 | [RB][FE][Contacts] Fix pagination bug on contact list | 2,50 |  | FIXED | 2026-05-14T10:00:00.000+0100 | FAUX
2026-05-15 | Aziz | FE | LIBRB | LIBRB-1200 | [RB][May KYC scope] | LIBRB-1201 | [RB][FE][KYC] May frontend integration | LIBRB-5811 | [RB][FE][KYC] Add biometric verification UI | 6,00 |  | In Progress | 2026-05-15T09:00:00.000+0100 | FAUX
2026-05-04 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2201 | [RB][BE][KYC] Customer APIs | LIBRB-5901 | [RB][BE] Create customer validation endpoint | 6,00 |  | Done | 2026-05-04T09:00:00.000+0100 | FAUX
2026-05-05 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2201 | [RB][BE][KYC] Customer APIs | LIBRB-5902 | [RB][BE] Add validation rules to customer endpoint | 4,50 |  | To Be Tested | 2026-05-05T10:00:00.000+0100 | FAUX
2026-05-06 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2202 | [RB][BE][Documents] Document APIs | LIBRB-5903 | [RB][BE] Fix document upload API | 3,50 |  | To Be Tested | 2026-05-06T09:45:00.000+0100 | FAUX
2026-05-07 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2202 | [RB][BE][Documents] Document APIs | LIBRB-5904 | [RB][BE] Improve document download performance | 6,00 |  | In Progress | 2026-05-07T09:30:00.000+0100 | FAUX
2026-05-08 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2203 | [RB][BE][Security] Access control | LIBRB-5905 | [RB][BE] Add role based access checks | 5,00 |  | To Be Tested | 2026-05-08T11:00:00.000+0100 | FAUX
2026-05-11 | Sami | BE | LIBRB | LIBRB-2210 | [RB][May Analytics scope] | LIBRB-2211 | [RB][BE][Analytics] Data aggregation | LIBRB-5906 | [RB][BE] Create analytics data aggregation service | 5,50 |  | In Progress | 2026-05-11T09:00:00.000+0100 | FAUX
2026-05-12 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2204 | [RB][BE][Notifications] Webhook APIs | LIBRB-5907 | [RB][BE] Add webhook notification endpoint | 4,00 |  | Done | 2026-05-12T09:30:00.000+0100 | FAUX
2026-05-13 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2205 | [RB][BE][Reports] Export APIs | LIBRB-5908 | [RB][BE] Implement batch export API for reports | 6,50 |  | To Be Tested | 2026-05-13T09:00:00.000+0100 | FAUX
2026-05-14 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2202 | [RB][BE][Documents] Document APIs | LIBRB-5909 | [RB][BE] Fix concurrency issue on document upload | 3,00 |  | FIXED | 2026-05-14T10:15:00.000+0100 | FAUX
2026-05-15 | Sami | BE | LIBRB | LIBRB-2200 | [RB][May Backend APIs] | LIBRB-2203 | [RB][BE][Security] Access control | LIBRB-5910 | [RB][BE][Security] Add audit logging for admin actions | 5,00 |  | In Progress | 2026-05-15T09:00:00.000+0100 | FAUX
2026-05-04 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3201 | [RB][QA] KYC test plan | LIBRB-6001 | [RB][QA] Prepare May KYC test plan | 3,00 |  | Done | 2026-05-04T10:00:00.000+0100 | FAUX
2026-05-05 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3201 | [RB][QA] KYC test plan | LIBRB-6002 | [RB][QA] Execute KYC validation tests | 5,50 |  | Done | 2026-05-05T09:15:00.000+0100 | FAUX
2026-05-06 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3202 | [RB][QA] Contact module testing | LIBRB-6003 | [RB][QA] Validate contact translation fixes | 2,50 |  | Done | 2026-05-06T13:00:00.000+0100 | FAUX
2026-05-07 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3202 | [RB][QA] Contact module testing | LIBRB-6004 | [RB][QA] Retest frontend bug fixes | 3,00 |  | Done | 2026-05-07T11:00:00.000+0100 | FAUX
2026-05-08 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3203 | [RB][QA] Regression testing | LIBRB-6005 | [RB][QA] Regression test cycle for May release | 5,00 |  | Done | 2026-05-08T09:30:00.000+0100 | FAUX
2026-05-11 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3204 | [RB][QA] Dashboard testing | LIBRB-6006 | [RB][QA] Test analytics overview page | 3,50 |  | Done | 2026-05-11T09:00:00.000+0100 | FAUX
2026-05-12 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3204 | [RB][QA] Dashboard testing | LIBRB-6007 | [RB][QA] Validate notification badge behavior | 4,00 |  | Done | 2026-05-12T09:30:00.000+0100 | FAUX
2026-05-13 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3205 | [RB][QA] API testing | LIBRB-6008 | [RB][QA] Test batch export API | 5,00 |  | In Progress | 2026-05-13T09:15:00.000+0100 | FAUX
2026-05-14 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3205 | [RB][QA] API testing | LIBRB-6009 | [RB][QA] Security audit log validation | 3,50 |  | Done | 2026-05-14T10:00:00.000+0100 | FAUX
2026-05-15 | Nour | QA | LIBRB | LIBRB-3200 | [RB][May Testing] | LIBRB-3203 | [RB][QA] Regression testing | LIBRB-6010 | [RB][QA] End-to-end regression for May sprint 2 | 6,00 |  | Done | 2026-05-15T09:00:00.000+0100 | FAUX
2026-05-01 | Aziz | FE | LIBRB |  |  |  |  | LIBRB-HOL-0501 | Public holiday - Labour Day | 0,00 | Labour Day | Holiday | 2026-05-01T00:00:00.000+0100 | FAUX
2026-05-25 | Aziz | FE | LIBRB |  |  |  |  | LIBRB-HOL-0525 | Public holiday - Eid al-Adha | 0,00 | Eid al-Adha | Holiday | 2026-05-25T00:00:00.000+0100 | FAUX
2026-04-30 | Aziz | FE | LIBRB | LIBRB-1100 | [RB][April scope] | LIBRB-1101 | April frontend support | LIBRB-5701 | April frontend support task | 6,00 |  | Done | 2026-04-30T09:00:00.000+0100 | FAUX
2026-06-01 | Sami | BE | LIBRB | LIBRB-2300 | [RB][June scope] | LIBRB-2301 | June backend kickoff | LIBRB-6101 | June backend kickoff task | 7,00 |  | In Progress | 2026-06-01T09:00:00.000+0100 | FAUX

## Expected_Results
Metric | Value | Unit
Expected monthly_total_hours for 2026-05 | 134 | hours
Expected Total MD for 2026-05 | 16.75 | MD
Rows counted for 2026-05 | 33 | rows

## Expected_By_Role
Role | Time_Hours | Total_MD
BE | 49 | 6.12
FE | 44 | 5.5
QA | 41 | 5.12