## Jira_Data
Date | Author | Role | Project | Parent Epic | Parent Epic Summary | Parent Ticket | Parent Summary | Ticket | Summary | Time (h) | Holiday | Status | Started | Weekend
2026-02-28 | Nour | QA | LIBRB | LIBRB-2900 | [RB][February Testing] | LIBRB-2901 | [RB][QA] February final regression | LIBRB-5399 | [RB][QA] Final regression cycle for February release | 5,00 |  | Done | 2026-02-28T09:00:00.000+0100 | FAUX
2026-03-02 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1001 | [RB][FE][KYC] March frontend integration | LIBRB-5401 | [RB][FE][KYC] Setup KYC module project structure | 4,00 |  | Done | 2026-03-02T09:00:00.000+0100 | FAUX
2026-03-03 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1001 | [RB][FE][KYC] March frontend integration | LIBRB-5402 | [RB][FE][KYC] Create personal information form | 5,50 |  | Done | 2026-03-03T09:30:00.000+0100 | FAUX
2026-03-04 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1002 | [RB][FE][KYC] Document upload components | LIBRB-5403 | [RB][FE][KYC] Build drag and drop file uploader | 6,00 |  | FIXED | 2026-03-04T09:00:00.000+0100 | FAUX
2026-03-05 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1002 | [RB][FE][KYC] Document upload components | LIBRB-5404 | [RB][FE][KYC] Add file size and type validation | 3,50 |  | Done | 2026-03-05T10:00:00.000+0100 | FAUX
2026-03-06 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1001 | [RB][FE][KYC] March frontend integration | LIBRB-5405 | [RB][FE][KYC] Integrate address autocomplete API | 4,50 |  | To Be Tested | 2026-03-06T09:15:00.000+0100 | FAUX
2026-03-09 | Aziz | FE | LIBRB | LIBRB-1010 | [RB][Contacts March improvements] | LIBRB-1011 | [RB][FE][Contacts] Search and filter enhancements | LIBRB-5406 | [RB][FE][Contacts] Add advanced search with multiple criteria | 5,00 |  | In Progress | 2026-03-09T09:00:00.000+0100 | FAUX
2026-03-10 | Aziz | FE | LIBRB | LIBRB-1010 | [RB][Contacts March improvements] | LIBRB-1011 | [RB][FE][Contacts] Search and filter enhancements | LIBRB-5407 | [RB][FE][Contacts] Implement export contacts to CSV | 4,00 |  | Done | 2026-03-10T09:30:00.000+0100 | FAUX
2026-03-11 | Aziz | FE | LIBRB | LIBRB-1010 | [RB][Contacts March improvements] | LIBRB-1012 | [RB][FE][Contacts] Contact detail page | LIBRB-5408 | [RB][FE][Contacts] Redesign contact detail sidebar | 3,50 |  | FIXED | 2026-03-11T10:00:00.000+0100 | FAUX
2026-03-12 | Aziz | FE | LIBRB | LIBRB-1020 | [RB][March Onboarding scope] | LIBRB-1021 | [RB][FE][Onboarding] Welcome wizard | LIBRB-5409 | [RB][FE][Onboarding] Build multi-step welcome wizard | 6,50 |  | In Progress | 2026-03-12T09:00:00.000+0100 | FAUX
2026-03-13 | Aziz | FE | LIBRB | LIBRB-1020 | [RB][March Onboarding scope] | LIBRB-1021 | [RB][FE][Onboarding] Welcome wizard | LIBRB-5410 | [RB][FE][Onboarding] Add progress tracker to wizard | 4,00 |  | To Be Tested | 2026-03-13T09:15:00.000+0100 | FAUX
2026-03-16 | Aziz | FE | LIBRB | LIBRB-1020 | [RB][March Onboarding scope] | LIBRB-1022 | [RB][FE][Onboarding] Profile setup page | LIBRB-5411 | [RB][FE][Onboarding] Create profile photo upload component | 3,00 |  | Done | 2026-03-16T09:00:00.000+0100 | FAUX
2026-03-17 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1002 | [RB][FE][KYC] Document upload components | LIBRB-5412 | [RB][FE][KYC] Fix preview display for PDF documents | 2,50 |  | FIXED | 2026-03-17T13:00:00.000+0100 | FAUX
2026-03-18 | Aziz | FE | LIBRB | LIBRB-1010 | [RB][Contacts March improvements] | LIBRB-1012 | [RB][FE][Contacts] Contact detail page | LIBRB-5413 | [RB][FE][Contacts] Add activity timeline to contact detail | 5,00 |  | In Progress | 2026-03-18T09:00:00.000+0100 | FAUX
2026-03-19 | Aziz | FE | LIBRB | LIBRB-1020 | [RB][March Onboarding scope] | LIBRB-1022 | [RB][FE][Onboarding] Profile setup page | LIBRB-5414 | [RB][FE][Onboarding] Implement role selection during setup | 4,50 |  | Done | 2026-03-19T09:30:00.000+0100 | FAUX
2026-03-20 | Aziz | FE | LIBRB |  |  |  |  | LIBRB-HOL-0320 | Independence Day - Public Holiday | 0,00 | Independence Day | Holiday | 2026-03-20T00:00:00.000+0100 | FAUX
2026-03-23 | Aziz | FE | LIBRB | LIBRB-1000 | [RB][March KYC scope] | LIBRB-1001 | [RB][FE][KYC] March frontend integration | LIBRB-5415 | [RB][FE][KYC] Add real-time form validation feedback | 5,50 |  | To Be Tested | 2026-03-23T09:00:00.000+0100 | FAUX
2026-03-24 | Aziz | FE | LIBRB | LIBRB-1020 | [RB][March Onboarding scope] | LIBRB-1021 | [RB][FE][Onboarding] Welcome wizard | LIBRB-5416 | [RB][FE][Onboarding] Fix wizard navigation back button bug | 3,00 |  | FIXED | 2026-03-24T10:00:00.000+0100 | FAUX
2026-03-25 | Aziz | FE | LIBRB | LIBRB-1010 | [RB][Contacts March improvements] | LIBRB-1011 | [RB][FE][Contacts] Search and filter enhancements | LIBRB-5417 | [RB][FE][Contacts] Optimize contact list lazy loading | 4,00 |  | Done | 2026-03-25T09:00:00.000+0100 | FAUX
2026-03-02 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2001 | [RB][BE][KYC] Identity APIs | LIBRB-5451 | [RB][BE] Create identity verification endpoint | 5,00 |  | Done | 2026-03-02T09:00:00.000+0100 | FAUX
2026-03-03 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2001 | [RB][BE][KYC] Identity APIs | LIBRB-5452 | [RB][BE] Add OCR integration for document parsing | 6,00 |  | In Progress | 2026-03-03T09:30:00.000+0100 | FAUX
2026-03-04 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2002 | [RB][BE][Contacts] Contact APIs | LIBRB-5453 | [RB][BE] Create bulk contact import API | 5,50 |  | Done | 2026-03-04T09:00:00.000+0100 | FAUX
2026-03-05 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2002 | [RB][BE][Contacts] Contact APIs | LIBRB-5454 | [RB][BE] Add deduplication logic to contact import | 4,00 |  | To Be Tested | 2026-03-05T10:00:00.000+0100 | FAUX
2026-03-06 | Sami | BE | LIBRB | LIBRB-2010 | [RB][March Infrastructure scope] | LIBRB-2011 | [RB][BE][Infra] Database optimization | LIBRB-5455 | [RB][BE] Optimize slow queries on customer table | 4,50 |  | FIXED | 2026-03-06T09:15:00.000+0100 | FAUX
2026-03-09 | Sami | BE | LIBRB | LIBRB-2010 | [RB][March Infrastructure scope] | LIBRB-2011 | [RB][BE][Infra] Database optimization | LIBRB-5456 | [RB][BE] Add database indexes for search performance | 3,50 |  | Done | 2026-03-09T09:00:00.000+0100 | FAUX
2026-03-10 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2001 | [RB][BE][KYC] Identity APIs | LIBRB-5457 | [RB][BE] Add retry mechanism to OCR service calls | 5,00 |  | In Progress | 2026-03-10T09:30:00.000+0100 | FAUX
2026-03-11 | Sami | BE | LIBRB | LIBRB-2010 | [RB][March Infrastructure scope] | LIBRB-2012 | [RB][BE][Infra] Caching layer | LIBRB-5458 | [RB][BE] Implement Redis caching for session management | 6,50 |  | Done | 2026-03-11T09:00:00.000+0100 | FAUX
2026-03-12 | Sami | BE | LIBRB | LIBRB-2010 | [RB][March Infrastructure scope] | LIBRB-2012 | [RB][BE][Infra] Caching layer | LIBRB-5459 | [RB][BE] Add cache invalidation for customer updates | 4,00 |  | To Be Tested | 2026-03-12T09:45:00.000+0100 | FAUX
2026-03-13 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2003 | [RB][BE][Onboarding] Onboarding APIs | LIBRB-5460 | [RB][BE] Create onboarding workflow API | 5,50 |  | In Progress | 2026-03-13T09:00:00.000+0100 | FAUX
2026-03-14 | Sami | BE | LIBRB |  |  |  |  | LIBRB-5461 | Weekend support for urgent backend hotfix | 2,00 |  | FIXED | 2026-03-14T11:00:00.000+0100 | VRAI
2026-03-16 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2003 | [RB][BE][Onboarding] Onboarding APIs | LIBRB-5462 | [RB][BE] Add email notification trigger on onboarding | 4,50 |  | Done | 2026-03-16T09:00:00.000+0100 | FAUX
2026-03-17 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2001 | [RB][BE][KYC] Identity APIs | LIBRB-5463 | [RB][BE] Fix timeout issue on identity verification | 3,00 |  | FIXED | 2026-03-17T10:00:00.000+0100 | FAUX
2026-03-18 | Sami | BE | LIBRB | LIBRB-2010 | [RB][March Infrastructure scope] | LIBRB-2011 | [RB][BE][Infra] Database optimization | LIBRB-5464 | [RB][BE] Migrate legacy stored procedures to ORM | 7,00 |  | In Progress | 2026-03-18T09:00:00.000+0100 | FAUX
2026-03-19 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2002 | [RB][BE][Contacts] Contact APIs | LIBRB-5465 | [RB][BE] Add pagination to contact search endpoint | 4,00 |  | Done | 2026-03-19T09:30:00.000+0100 | FAUX
2026-03-23 | Sami | BE | LIBRB | LIBRB-2000 | [RB][March Backend APIs] | LIBRB-2003 | [RB][BE][Onboarding] Onboarding APIs | LIBRB-5466 | [RB][BE] Add progress tracking to onboarding workflow | 5,50 |  | To Be Tested | 2026-03-23T09:00:00.000+0100 | FAUX
2026-03-02 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3001 | [RB][QA] KYC module testing | LIBRB-5501 | [RB][QA] Prepare March KYC test plan | 3,50 |  | Done | 2026-03-02T09:00:00.000+0100 | FAUX
2026-03-03 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3001 | [RB][QA] KYC module testing | LIBRB-5502 | [RB][QA] Execute identity verification tests | 4,50 |  | Done | 2026-03-03T09:30:00.000+0100 | FAUX
2026-03-04 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3001 | [RB][QA] KYC module testing | LIBRB-5503 | [RB][QA] Test document upload drag and drop | 3,00 |  | Done | 2026-03-04T10:00:00.000+0100 | FAUX
2026-03-05 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3002 | [RB][QA] Contact module testing | LIBRB-5504 | [RB][QA] Test bulk contact import functionality | 4,00 |  | Done | 2026-03-05T09:00:00.000+0100 | FAUX
2026-03-06 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3002 | [RB][QA] Contact module testing | LIBRB-5505 | [RB][QA] Validate contact deduplication logic | 3,50 |  | In Progress | 2026-03-06T09:15:00.000+0100 | FAUX
2026-03-09 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3003 | [RB][QA] Infrastructure testing | LIBRB-5506 | [RB][QA] Performance test on optimized queries | 5,00 |  | Done | 2026-03-09T09:00:00.000+0100 | FAUX
2026-03-10 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3003 | [RB][QA] Infrastructure testing | LIBRB-5507 | [RB][QA] Test Redis caching behavior | 4,00 |  | Done | 2026-03-10T09:30:00.000+0100 | FAUX
2026-03-11 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3001 | [RB][QA] KYC module testing | LIBRB-5508 | [RB][QA] Retest file validation bug fixes | 2,50 |  | Done | 2026-03-11T11:00:00.000+0100 | FAUX
2026-03-12 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3004 | [RB][QA] Onboarding testing | LIBRB-5509 | [RB][QA] Write test cases for onboarding wizard | 4,50 |  | In Progress | 2026-03-12T09:00:00.000+0100 | FAUX
2026-03-13 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3004 | [RB][QA] Onboarding testing | LIBRB-5510 | [RB][QA] Execute onboarding workflow tests | 3,50 |  | Done | 2026-03-13T09:30:00.000+0100 | FAUX
2026-03-16 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3002 | [RB][QA] Contact module testing | LIBRB-5511 | [RB][QA] Test contact export to CSV feature | 3,00 |  | Done | 2026-03-16T09:00:00.000+0100 | FAUX
2026-03-17 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3004 | [RB][QA] Onboarding testing | LIBRB-5512 | [RB][QA] Validate email notifications on onboarding | 4,00 |  | To Be Tested | 2026-03-17T10:00:00.000+0100 | FAUX
2026-03-18 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3005 | [RB][QA] Regression testing | LIBRB-5513 | [RB][QA] Mid-March regression test cycle | 5,50 |  | Done | 2026-03-18T09:00:00.000+0100 | FAUX
2026-03-19 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3003 | [RB][QA] Infrastructure testing | LIBRB-5514 | [RB][QA] Test cache invalidation scenarios | 3,50 |  | Done | 2026-03-19T09:30:00.000+0100 | FAUX
2026-03-23 | Nour | QA | LIBRB | LIBRB-3000 | [RB][March Testing] | LIBRB-3005 | [RB][QA] Regression testing | LIBRB-5515 | [RB][QA] Final regression test cycle for March release | 6,00 |  | Done | 2026-03-23T09:00:00.000+0100 | FAUX
2026-04-01 | Aziz | FE | LIBRB | LIBRB-1100 | [RB][April KYC scope] | LIBRB-1101 | [RB][FE][KYC] April frontend integration | LIBRB-5601 | [RB][FE][KYC] Build KYC document upload form | 5,00 |  | In Progress | 2026-04-01T09:00:00.000+0100 | FAUX

## Expected_Results
Metric | Value | Unit
Expected monthly_total_hours for 2026-03 | 209.5 | hours
Expected Total MD for 2026-03 | 26.19 | MD
Rows counted for 2026-03 | 49 | rows

## Expected_By_Role
Role | Time_Hours | Total_MD
BE | 75.5 | 9.44
FE | 74 | 9.25
QA | 60 | 7.5